## log
vdate | name | notes
2014-12-11 | Melissa Ramlakhan | 48 Hr Meeting Scheduled for 12.16 | 30
2014-12-17 | Melissa Ramlakhan | 72 Hr Meeting Scheduled for 12.19 | 30
2014-12-23 | Melissa Ramlakhan | Nash sent over work proposal | 30
2014-12-24 | Melissa Ramlakhan | 96 Hr meeting is scheduled | 30
2014-12-19 | Melissa Ramlakhan | Nash meeting with Ron on 12.30 at 10:30 to discuss the project. Ron asked to reschedule | 30
2014-12-30 | Melissa Ramlakhan | Heidi sent survey to Nash. Nash is waiting to discuss with Ron | 30
2015-01-14 | Heidi Velovic | Retained Nash | 46
2015-01-14 | Heidi Velovic | Nash is going to go to the property to survey it today. Will follow up later on today | 46
2015-01-15 | Melissa Ramlakhan | Sent follow up email to Nash | 30
2015-01-28 | Melissa Ramlakhan | nash sent revised layout 1/28 ron and edi need to review | 30
2015-03-11 | Jamie Ventura | revised the plan yesterday and sent already to our mechanical engineer to proceed - working dob plans now will have ready in two weeks…..i am working on soil perc test ,TR1,TR8(once Nash forwards to me) … virtual meeting with the HUB unit this coming Friday 3/13 to introduce the job to them and file with them after.….. Edi will have ,lighting roof layout, front of the building design and interior by monday then Bobby will get me bids *****HVAC model numbers, bids from bobby, need mechanical drawings - send to rob | 26
2015-03-18 | Jamie Ventura | HUB will accept the Job. They had some comments on the plans, some of them are minor and easy to fix, but the main one is regarding to the mechanical room doors that we have open on the exit corridor at the upper floors, which we can easily flip the doors inside the units to resolve that issue, and flip the kitchen layout so we don't lose the area. next step will be emailing the PW1 form, they Enter the job, then we pay for it and upload all the reacquired documents for filing including the plans. After this process completion, they will send us another invitation to review the project in details, go over the drawings with the assigned plan examiner, then they review the job and disapprove it with their comments. After a few meetings with them to resolve the open issues we obtain the approval and get you the permits. This project will not require an ACP5 because it's a new building. following items, not prior to filing but prior to approval: - TR1 ( technical inspection report) & Tr2,Tr3 ( concrete testing and inspection)& Tr8 ( energy inspections) - Exhibits I& III | 26
2015-03-18 | Jamie Ventura | We will file our Pw1 max by tomorrow, it well take a few days after to know when is our 1st meeting with them. After getting the filing done, It depends on how busy is the assigned plan examiner, I would say 3 weeks more or less between each appointment. We had our meeting today in person, we have the option to do our meetings online or in person. | 26
2015-03-20 | Jamie Ventura | meeting to go over bids with ron and bobby today | 26
2015-03-24 | Jamie Ventura | sent plans to get a take off as per rons request, edi is sending form 6 in the next day…..bobby and ron need to meet again ron wants a very detailed budget and bobby works better on a % based agreemernt | 26
2015-04-03 | Jamie Ventura | received take off - scheduleing for a walk through with Jon from scott schnall's office so we can get TR's initialed and confirm price | 26
2015-04-15 | Jamie Ventura | no one on site | 26
2015-04-07 | Jamie Ventura | next plan exam date scheduled 5/7/2015 @ 2pm - need to arrange a walk through with scott schnall office to move forward with TR's | 26
2015-04-21 | Jamie Ventura | Plan exam date 5/7 will have a better update then in the meantime lets get the budget set with Bobby so were ready to take off immediately after getting the green light | 26
2015-04-29 | Jamie Ventura | plan exam date coming up, Alon mailing original TRs to Nash office , pushing Ron to sit with Bobby and go over budget | 26
2015-05-01 | Jamie Ventura | daniel joshua - I'm about $150/$175 per square foot to build. Remodeling could be around $120 per square foot. | 26
2015-05-04 | Jamie Ventura | Their are some many things involved with this building including site safety, sidewalk bridging, additional filings, etc. I personally would only hire a contractor that has done a project of this size and complexity before. If you hire a contractor that doesn't have experience with this kind of work, it will be difficult and they will be learning on your project. Also, please make sure whichever contractor you hire that they have sufficient insurance and they MUST add you as owner and NIS design and Robert M. Hanna, P.E. as addionally insured ( this doesn't cost the contractor anything) | 26
2015-05-05 | Jamie Ventura | We’re filing a ALT1 extending in the back and adding a floor on the top. We’re changing the number of dwelling units | 26
2015-05-07 | Jamie Ventura | Looking at 6300 square feet. Total job I can demo and rebuild at $90 per square foot (plumbing or electric or mechanical not included) (materials are included) (appliances not included) $130 per square foot and it'll include everything including sprinklers all plumbing all electric all demo all carpentry all installation of any appliances - (appliances not included) | 26
2015-05-08 | Jamie Ventura | Please be advised that we had our first meeting with the plan examiner for the JOB Yesterday, and he had some minor comments on the drawings and the paperwork, he will work on the official comments and send them to us. Also We need to change the construction classification of the building from (II) to (I) in order for us to get away with one staircase as one exit, which means we will need to use concrete for our floor slabs as a non-combustible material and remove the plywood. | 26
2015-05-09 | Jamie Ventura | We are looking for concrete planks to put on top of the beams that can do the same job | 26
2015-05-22 | Jamie Ventura | Bainbridge was finally disapproved, but we didn't get the comments yet, we will try to contact the HUB today for the comments | 26
| Jamie Ventura | plans approval pending zoning approval which you do not have yet | 26
2015-05-26 | Jamie Ventura | We got to work on the comments and revise all the plans before we can schedule a meeting We will try to wrap it up and request a meting by the end of the week We suggest to remove all seating areas and fire pits from the roof level to get red of some comments | 26
2015-06-01 | Jamie Ventura | need the updated tr1 forms for the soil investigation report sign on and off. Please be adivsed that fire alarm system is required by the new code 2008 for Buildings more than 3 stories in height in residintail use more than 2 family. It will not delay the approval, but it might delay the permit, please advise if you have someone to design it and file it for you other wise I know someone. | 26
2015-06-05 | Jamie Ventura | It will be $2,000 of total price to include the system design, filing with fire dept. and obtaining work permit | 26
2015-06-11 | Jamie Ventura | plan appointment is on July 10th. | 26
2015-06-15 | Jamie Ventura | Looks like meters were outside but removed. No access to basement. 3rd floor is cleaned up 1 and 2 are full of garbage. | 26
2015-06-19 | Jamie Ventura | My engineer just finish the Draft ,we will draw it, will send it to you with the required documents to sign by next week | 26
2015-06-22 | Jamie Ventura | please find our PW1 form& Pw3 for filing the fire alarm system, please get me the signed pw1 form& Pw3 form has to be signed and notarized Also I will need the following checks for filing; $471.00 payable to" NYC dept of Buildings" $165 for the work permit payable to" NYC dept of Buildings" $1000 for NIS Design as the retainer You should get the final drawings for the fire alarm system early this week | 26
2015-07-07 | Jamie Ventura | approval for the RPZ device from DEP & new water service for the fire line | 26
2015-07-10 | Jamie Ventura | Hi Ron, We are happy to inform you that our meeting today for Bainbridge went very well, we removed all the objections except one objection which is related to stairs doorway clearance. We will revise the plans and resubmit ASAP to get another appt, we should obtain the approval in our next meeting. | 26
2015-07-11 | Jamie Ventura | Ychay Simkhai - I met with Ron this morning and discussed numbers. He asked I hold off on that until we lock down on Warren St first. | 26
2015-07-16 | Jamie Ventura | find the 10 Days notice letters for the adjacent properties Please print two copies of each letter, sign them by the owner, use certified mail to mail them out to the adjacent property, send me back the second signed copies with the mailing receipts You can also scan and mail them back to me | 26
2015-07-20 | Jamie Ventura | ron is requesting bid from albert on consrtuction, still waiting on bid from ardi.It's Aug the 4th is the next plan exam date Please get me the 10 days notice letters so I can have the plan examiner remove this item. | 26
2015-07-23 | Jamie Ventura | ron got a proposal from ardi requested for ron to email to me | 26
2015-07-27 | Jamie Ventura | confirmed with nash plan exam is scheduled for 8/4 nothing needed on my end before then | 26
2015-08-06 | Jamie Ventura | all the open comments have been cleared today, however, the examiner wanted to increase the job construction cost prior to approval, he feels that 358k is too low We submitted a request already to increase the construction cost with the amount that he requested, and we will email the examiner to approve the job once it's done Hopefully it will be done before he leaves for his vacation this week other wise we will have to wait another two weeks. I will keep you updated. | 26
2015-08-10 | Jamie Ventura | The last thing the plan examiner wanted to see before he approves the job was to revise the project cost, which we did, but it seams like he went to his vacation before he approves the Job | 26
2015-08-12 | Jamie Ventura | plan examiner didn’t reply back he wont be back before next week, I will put a request for another meeting just in case - need ron to make a decision which GC we will move forward with | 26
2015-08-17 | Jamie Ventura | ron is reaching out to GC to hire | 26
2015-08-04 | Jamie Ventura | I just wanted to let you know that all the open comments have been cleared today, however, the examiner wanted to increase the job construction cost prior to approval, he feels that 358k is too low We submitted a request already to increase the construction cost with the amount that he requested, and we will email the examiner to approve the job once it's done Hopefully it will be done before he leaves for his vacation this week other wise we will have to wait another two weeks. I will keep you updated. | 26
2015-08-10 | Jamie Ventura | The last thing the plan examiner wanted to see before he approves the job was to revise the project cost, which we did, but it seams like he went to his vacation before he approves the Job I will email him again this morning and let you know. | 26
2015-08-14 | Jamie Ventura | The examiner is still on vacation, but I scheduled another meeting to play it safe and I got it on Sep 17 I will try to reach him again next week | 26
2015-08-19 | Jamie Ventura | simcha - Place cleaned up | 26
2015-08-24 | Jamie Ventura | two appointments with two new contractors this week | 26
2015-08-31 | Jamie Ventura | job was finally approved today ! Need to quiclkly pull permits and start work | 26
2015-09-03 | Jamie Ventura | Noone on site, no progress since last time. Seems 433 garbage is ending up here. | 26
2015-09-08 | Jamie Ventura | waiting on ron to make a decision on which GC to use…….vio# 34469092X,34930212Y,35029160X has been cured and paid | 26
2015-09-14 | Jamie Ventura | followed up with ron again to try to move the project along | 26
2015-09-16 | Jamie Ventura | received proposal from jenny flores for $475…..ron requested nash to pull permits under ardit | 26

## Sheet1
Notes Spreadsheet
Activity LOG
Property Address | Date | Comments | name | Date
|  | 48 Hr Meeting Scheduled for 12.16 | Melissa | 2014-12-11 | Melissa Ramlakhan
|  | 72 Hr Meeting Scheduled for 12.19 | melissa | 2014-12-17 | Melissa Ramlakhan
|  | 12.23 Nash sent over work proposal | melissa |  | Melissa Ramlakhan
|  | 96 Hr meeting is scheduled | melissa | 2014-12-24 | Melissa Ramlakhan
|  | Nash meeting with Ron on 12.30 at 10:30 to discuss the project. Ron asked to reschedule | melissa | 2014-12-19 | Melissa Ramlakhan
|  | Heidi sent survey to Nash. Nash is waiting to discuss with Ron | melissa | 2014-12-30 | Melissa Ramlakhan
431 Bainbridge St |  | Retained Nash | Heidi | 2015-01-14 | Heidi Velovic
|  | Nash is going to go to the property to survey it today. Will follow up later on today | Heidi | 2015-01-14 | Heidi Velovic
|  | Sent follow up email to Nash | Melissa | 2015-01-15 | Melissa Ramlakhan
nash sent revised layout 1/28 ron and edi need to review
|  | revised the plan yesterday and sent already to our mechanical engineer to proceed - working dob plans now will have ready in two weeks…..i am working on soil perc test ,TR1,TR8(once Nash forwards to me) … virtual meeting with the HUB unit this coming Friday 3/13 to introduce the job to them and file with them after.….. Edi will have ,lighting roof layout, front of the building design and interior by monday then Bobby will get me bids *****HVAC model numbers, bids from bobby, need mechanical drawings - send to rob | jamie | 2015-03-11 | Jamie Ventura
|  | HUB will accept the Job. They had some comments on the plans, some of them are minor and easy to fix, but the main one is regarding to the mechanical room doors that we have open on the exit corridor at the upper floors, which we can easily flip the doors inside the units to resolve that issue, and flip the kitchen layout so we don't lose the area. next step will be emailing the PW1 form, they Enter the job, then we pay for it and upload all the reacquired documents for filing including the plans. After this process completion, they will send us another invitation to review the project in details, go over the drawings with the assigned plan examiner, then they review the job and disapprove it with their comments. After a few meetings with them to resolve the open issues we obtain the approval and get you the permits. This project will not require an ACP5 because it's a new building. following items, not prior to filing but prior to approval: - TR1 ( technical inspection report) & Tr2,Tr3 ( concrete testing and inspection)& Tr8 ( energy inspections) - Exhibits I& III | jamie | 2015-03-18 | Jamie Ventura
|  | We will file our Pw1 max by tomorrow, it well take a few days after to know when is our 1st meeting with them. After getting the filing done, It depends on how busy is the assigned plan examiner, I would say 3 weeks more or less between each appointment. We had our meeting today in person, we have the option to do our meetings online or in person. | jamie | 2015-03-18 | Jamie Ventura
|  | meeting to go over bids with ron and bobby today | jamie | 2015-03-20 | Jamie Ventura
|  | sent plans to get a take off as per rons request, edi is sending form 6 in the next day…..bobby and ron need to meet again ron wants a very detailed budget and bobby works better on a % based agreemernt | jamie | 2015-03-24 | Jamie Ventura
|  | received take off - scheduleing for a walk through with Jon from scott schnall's office so we can get TR's initialed and confirm price | jamie | 2015-04-03 | Jamie Ventura
|  | no one on site | jamie | 2015-04-15 | Jamie Ventura
|  | next plan exam date scheduled 5/7/2015 @ 2pm - need to arrange a walk through with scott schnall office to move forward with TR's | jamie | 2015-04-07 | Jamie Ventura
|  | Plan exam date 5/7 will have a better update then in the meantime lets get the budget set with Bobby so were ready to take off immediately after getting the green light | jamie | 2015-04-21 | Jamie Ventura
|  | plan exam date coming up, Alon mailing original TRs to Nash office , pushing Ron to sit with Bobby and go over budget | jamie | 2015-04-29 | Jamie Ventura
|  | daniel joshua - I'm about $150/$175 per square foot to build. Remodeling could be around $120 per square foot. | jamie | 2015-05-01 | Jamie Ventura
|  | Their are some many things involved with this building including site safety, sidewalk bridging, additional filings, etc. I personally would only hire a contractor that has done a project of this size and complexity before. If you hire a contractor that doesn't have experience with this kind of work, it will be difficult and they will be learning on your project. Also, please make sure whichever contractor you hire that they have sufficient insurance and they MUST add you as owner and NIS design and Robert M. Hanna, P.E. as addionally insured ( this doesn't cost the contractor anything) | jamie | 2015-05-04 | Jamie Ventura
|  | We’re filing a ALT1 extending in the back and adding a floor on the top. We’re changing the number of dwelling units | jamie | 2015-05-05 | Jamie Ventura
|  | Looking at 6300 square feet. Total job I can demo and rebuild at $90 per square foot (plumbing or electric or mechanical not included) (materials are included) (appliances not included) $130 per square foot and it'll include everything including sprinklers all plumbing all electric all demo all carpentry all installation of any appliances - (appliances not included) | jamie | 2015-05-07 | Jamie Ventura
|  | Please be advised that we had our first meeting with the plan examiner for the JOB Yesterday, and he had some minor comments on the drawings and the paperwork, he will work on the official comments and send them to us. Also We need to change the construction classification of the building from (II) to (I) in order for us to get away with one staircase as one exit, which means we will need to use concrete for our floor slabs as a non-combustible material and remove the plywood. | jamie | 2015-05-08 | Jamie Ventura
|  | We are looking for concrete planks to put on top of the beams that can do the same job | jamie | 2015-05-09 | Jamie Ventura
|  | Bainbridge was finally disapproved, but we didn't get the comments yet, we will try to contact the HUB today for the comments | jamie | 2015-05-22 | Jamie Ventura
|  | plans approval pending zoning approval which you do not have yet | jamie |  | Jamie Ventura
|  | We got to work on the comments and revise all the plans before we can schedule a meeting We will try to wrap it up and request a meting by the end of the week We suggest to remove all seating areas and fire pits from the roof level to get red of some comments | jamie | 2015-05-26 | Jamie Ventura
|  | need the updated tr1 forms for the soil investigation report sign on and off. Please be adivsed that fire alarm system is required by the new code 2008 for Buildings more than 3 stories in height in residintail use more than 2 family. It will not delay the approval, but it might delay the permit, please advise if you have someone to design it and file it for you other wise I know someone. | jamie | 2015-06-01 | Jamie Ventura
|  | It will be $2,000 of total price to include the system design, filing with fire dept. and obtaining work permit | jamie | 2015-06-05 | Jamie Ventura
|  | plan appointment is on July 10th. | jamie | 2015-06-11 | Jamie Ventura
|  | Looks like meters were outside but removed. No access to basement. 3rd floor is cleaned up 1 and 2 are full of garbage. | jamie | 2015-06-15 | Jamie Ventura
|  | My engineer just finish the Draft ,we will draw it, will send it to you with the required documents to sign by next week | jamie | 2015-06-19 | Jamie Ventura
|  | please find our PW1 form& Pw3 for filing the fire alarm system, please get me the signed pw1 form& Pw3 form has to be signed and notarized Also I will need the following checks for filing; $471.00 payable to" NYC dept of Buildings" $165 for the work permit payable to" NYC dept of Buildings" $1000 for NIS Design as the retainer You should get the final drawings for the fire alarm system early this week | jamie | 2015-06-22 | Jamie Ventura
|  | approval for the RPZ device from DEP & new water service for the fire line | jamie | 2015-07-07 | Jamie Ventura
|  | Hi Ron, We are happy to inform you that our meeting today for Bainbridge went very well, we removed all the objections except one objection which is related to stairs doorway clearance. We will revise the plans and resubmit ASAP to get another appt, we should obtain the approval in our next meeting. | jamie | 2015-07-10 | Jamie Ventura
|  | Ychay Simkhai - I met with Ron this morning and discussed numbers. He asked I hold off on that until we lock down on Warren St first. | jamie | 2015-07-11 | Jamie Ventura
|  | find the 10 Days notice letters for the adjacent properties Please print two copies of each letter, sign them by the owner, use certified mail to mail them out to the adjacent property, send me back the second signed copies with the mailing receipts You can also scan and mail them back to me | jamie | 2015-07-16 | Jamie Ventura
|  | ron is requesting bid from albert on consrtuction, still waiting on bid from ardi.It's Aug the 4th is the next plan exam date Please get me the 10 days notice letters so I can have the plan examiner remove this item. | jamie | 2015-07-20 | Jamie Ventura
|  | ron got a proposal from ardi requested for ron to email to me | jamie | 2015-07-23 | Jamie Ventura
|  | confirmed with nash plan exam is scheduled for 8/4 nothing needed on my end before then | jamie | 2015-07-27 | Jamie Ventura
|  | all the open comments have been cleared today, however, the examiner wanted to increase the job construction cost prior to approval, he feels that 358k is too low We submitted a request already to increase the construction cost with the amount that he requested, and we will email the examiner to approve the job once it's done Hopefully it will be done before he leaves for his vacation this week other wise we will have to wait another two weeks. I will keep you updated. | jamie | 2015-08-06 | Jamie Ventura
|  | The last thing the plan examiner wanted to see before he approves the job was to revise the project cost, which we did, but it seams like he went to his vacation before he approves the Job | jamie | 2015-08-10 | Jamie Ventura
|  | plan examiner didn’t reply back he wont be back before next week, I will put a request for another meeting just in case - need ron to make a decision which GC we will move forward with | jamie | 2015-08-12 | Jamie Ventura
|  | ron is reaching out to GC to hire | jamie | 2015-08-17 | Jamie Ventura
|  | I just wanted to let you know that all the open comments have been cleared today, however, the examiner wanted to increase the job construction cost prior to approval, he feels that 358k is too low We submitted a request already to increase the construction cost with the amount that he requested, and we will email the examiner to approve the job once it's done Hopefully it will be done before he leaves for his vacation this week other wise we will have to wait another two weeks. I will keep you updated. | jamie | 2015-08-04 | Jamie Ventura
|  | The last thing the plan examiner wanted to see before he approves the job was to revise the project cost, which we did, but it seams like he went to his vacation before he approves the Job I will email him again this morning and let you know. | jamie | 2015-08-10 | Jamie Ventura
|  | The examiner is still on vacation, but I scheduled another meeting to play it safe and I got it on Sep 17 I will try to reach him again next week | jamie | 2015-08-14 | Jamie Ventura
|  | simcha - Place cleaned up | jamie | 2015-08-19 | Jamie Ventura
|  | two appointments with two new contractors this week | jamie | 2015-08-24 | Jamie Ventura
|  | job was finally approved today ! Need to quiclkly pull permits and start work | jamie | 2015-08-31 | Jamie Ventura
|  | Noone on site, no progress since last time. Seems 433 garbage is ending up here. | jamie | 2015-09-03 | Jamie Ventura
|  | waiting on ron to make a decision on which GC to use…….vio# 34469092X,34930212Y,35029160X has been cured and paid | jamie | 2015-09-08 | Jamie Ventura
|  | followed up with ron again to try to move the project along | jamie | 2015-09-14 | Jamie Ventura
|  | received proposal from jenny flores for $475…..ron requested nash to pull permits under ardit | jamie | 2015-09-16 | Jamie Ventura